## Sprint 1
Daily Scrum Report — Sprint 1
Kanban board is ZenHub. Use the ZenHub browser extension to view the RaiderNAV Kanban board in GitHub.
Meetings are for development team, and maybe scrum master.
Meetings will be conducted each Wednesday and Saturday, and over email if in-person meetings are not possible.
Each team member should report: what they have done, what they will do, and what impediments prevent them from progressing.
Meeting 1 | 7 Feb 18
| Arpit | What they have done: |  | Joined GitHub project
|  | What they will do: |  | Break down user stories 16-18 and 20. Install ZenHub. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Brody | What they have done: |  | Joined GitHub project and installed ZenHub.
|  | What they will do: |  | Break down user stories 4-6. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Michael | What they have done: |  | Joined GitHub project and installed ZenHub.
|  | What they will do: |  | Break down user stories 7-9. Product mockup. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Sakshyam | What they have done: |  | Joined GitHub project and installed ZenHub.
|  | What they will do: |  | Break down user stories 1-3. Product mockup. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Vasilis | What they have done: |  | Joined GitHub project and installed ZenHub.
|  | What they will do: |  | Break down user stories 13-15. Permission form. Other unscheduled documents.
What impediments prevent them from progressing:
| Yong | What they have done: |  | Joined GitHub project and installed ZenHub.
|  | What they will do: |  | Break down user stories 10-12 and 19. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
Meeting 2 | 10 Feb 18
| Arpit | What they have done: |  | Absent from meeting
|  | What will they do: |  | Learn how to do use cases, install UMLet, install Android Studio, install ZenHub
What impediments prevent them from progressing:
| Brody | What they have done: | Installed Androi | Installed Android Studio, reqs and use cases for 4-6, interview scripts
|  | What they will do: |  | Update interview script
|  | What impediments prevent them from progressing: |  | None
| Michael | What they have done: |  | Installed Android Studio, reqs and use cases for 7-9
|  | What they will do: |  | Mockup
|  | What impediments prevent them from progressing: |  | None
| Sakshyam | What they have done: |  | Installed Android Studio, reqs and use cases for 1-3
|  | What they will do: |  | Mockup
|  | What impediments prevent them from progressing: |  | None
| Vasilis | What they have done: |  | reqs and use cases for stories 13-15, permission form, created various documents
What they will do:
|  | What impediments prevent them from progressing: |  | None
| Yong | What they have done: |  | Installed Android Studio, reqs and use cases for 10-12 and 18-20
What they will do:
|  | What impediments prevent them from progressing: |  | None
Meeting 3 | 12 Feb 18
| Arpit | What they have done: |  | Installed Android Studio, Installed UMLet, Installed ZenHub, Installed GitKraken
|  | What they will do: |  | SRS document
|  | What impediments prevent them from progressing: |  | Not knowing how to do use cases
| Brody | What they have done:
|  | What they will do: |  | Focus Group document
|  | What impediments prevent them from progressing: |  | None
| Michael | What they have done: |  | Product Mockup
|  | What they will do: |  | Focus Group document
|  | What impediments prevent them from progressing: |  | None
| Sakshyam | What they have done: |  | Product Mockup
|  | What they will do: |  | Focus Group document
|  | What impediments prevent them from progressing: |  | None
| Vasilis | What they have done:
|  | What they will do: |  | SRS document
|  | What impediments prevent them from progressing: |  | None
| Yong | What they have done:
|  | What they will do: |  | SRS document
What impediments prevent them from progressing:
Meeting 4 | 13 Feb 18
| Arpit | What they have done: |  | Absent from meeting
What they will do:
What impediments prevent them from progressing:
| Brody | What they have done: |  | Focus Group document, SRS document
What they will do:
|  | What impediments prevent them from progressing: |  | None
| Michael | What they have done: |  | Focus Group document, SRS document
What they will do:
|  | What impediments prevent them from progressing: |  | None
| Sakshyam | What they have done: |  | Focus Group document, SRS document
What they will do:
|  | What impediments prevent them from progressing: |  | None
| Vasilis | What they have done: |  | SRS document
What they will do:
|  | What impediments prevent them from progressing: |  | None
| Yong | What they have done: |  | SRS document
What they will do:
|  | What impediments prevent them from progressing: |  | None
END OF SPRINT

## Sprint 2
Daily Scrum Report — Sprint 2
Kanban board is ZenHub. Use the ZenHub browser extension to view the RaiderNAV Kanban board in GitHub.
Meetings are for development team, product owner, and scrum master.
Each team member should report: what they have done, what they will do, and what impediments prevent them from progressing.
Meeting 1 | 2018-02-16
| Arpit | What they have done: Project Proposal Presentation
What they will do: Attend next meeting 2/18
What impediments prevent them from progressing: N/A
| Brody | What they have done: Update Kanban Board, Update Daily Scrum Report, Update Sprint Backlog
What they will do: What they will do: Attend next meeting 2/18
What impediments prevent them from progressing: N/A
| Michael | What they have done: Project Proposal Presentation
What they will do: Organize focus groups participants and meeting time
What impediments prevent them from progressing: N/A
| Sakshyam | What they have done: Update Product Backlog for start of Sprint 2
What they will do: Attend next meeting 2/18
What impediments prevent them from progressing: N/A
| Vasilis | What they have done: Project Propsosal Presentation
What they will do: Attend next meeting 2/18
What impediments prevent them from progressing: N/A
| Yong | What they have done: Project Proposal Presentation
What they will do: Attend next meeting 2/18
What impediments prevent them from progressing: N/A
Meeting 2 | 2018-02-18
| Arpit | What they have done: Attended meeting, planned presentation
What will they do: Implement driver code to utilize google maps API to generate route from provided schedule detail
What impediments prevent them from progressing: N/A
| Brody | What they have done: Attended meeting, planned presentation, planned sprint 2 product implementation, updated zenhub board, updated sprint backlog
What they will do: Implement data structure for mapping building prefixes to physical addresses
What impediments prevent them from progressing: N/A
| Michael | What they have done: Absent from meeting (with valid reason)
What they will do: Organize focus group participants and meeting time, Create user interface for recalling schedules, schedule selection, and detail display
What impediments prevent them from progressing: N/A
| Sakshyam | What they have done: Attended meeting, planned presentation, planned sprint 2 product implementation
What they will do: Create user interface for creating a schedule, adding classes, and saving a schedule
What impediments prevent them from progressing: N/A
| Vasilis | What they have done: Attended meeting, planned presentation, planned sprint 2 product implementation
What they will do: Implement backend functionality for saving and recalling saved schedules
What impediments prevent them from progressing: N/A
| Yong | What they have done: Attended meeting, planned presentation, planned sprint 2 product implementation
What they will do: Implement front end for route display after API calls to generate route
What impediments prevent them from progressing: N/A
Meeting 3 | 2018-02-23
| Arpit | What they have done: Completed focus group session
What they will do: Implement driver code to utilize google maps API to generate route from provided schedule detail
What impediments prevent them from progressing: Unfamiliarity with platforms/APIs
| Brody | What they have done: Completed Android Studio & Google Maps API tutorials, Completed focus group session, Implemented hashmap for building to address mapping
What they will do: Test hashmap functionality
What impediments prevent them from progressing: Busy schedule/other classwork, Unfamiliarity with platforms/APIs
| Michael | What they have done: Organized focus group participants, Completed focus group session, Led focus group interaction, Started edit schedule interface
What they will do: Continue working on app implementation
What impediments prevent them from progressing: Unfamiliarity with platforms/APIs
| Sakshyam | What they have done: Completed creating home screen, create schedule screen and settings screen and linked those screens with buttons from home screen.
What they will do: Work on user interface
What impediments prevent them from progressing: Has been sick.
| Vasilis | What they have done: Added Google maps API key to project, Created some basic activites for app, Implemented load/save for schedules
What they will do: Complete save/load schedule implementation
What impediments prevent them from progressing: Other classwork
| Yong | What they have done: Completed focus group session
What they will do: Continue working on app implementation
What impediments prevent them from progressing: Problems with Android Studio
END OF SPRINT

## Sprint 3
Daily Scrum Report — Sprint 3
Kanban board is ZenHub. Use the ZenHub browser extension to view the RaiderNAV Kanban board in GitHub.
Meetings are for development team, product owner, and scrum master.
Each team member should report: what they have done, what they will do, and what impediments prevent them from progressing.
Meeting 1 | 2018-03-02
| Arpit | What they have done: No work completed
What they will do: Begin implementation tasks (Maps API code calls) assigned previously, Create configuration management plan document
What impediments prevent them from progressing: Difficulty with implementation
| Brody | What they have done: Rewrote hashmap to utilize latitudinal and longitudal coordinates(addresses were not accurate enough)
What they will do: Complete sprint 2 review , team member report, & focus group document. Update sprint/product backlog at end of sprint. Complete first app release implementation. Create GRL & UCM models document.
What impediments prevent them from progressing: Difficulty with implementation, other classwork
| Michael | What they have done: Began working on user interface implementation
What they will do: Create domain model & detailed design document. Complete first app release implementation.
What impediments prevent them from progressing: Difficulty with implementation, other classwork
| Sakshyam | What they have done: Began working on user interface implementation
What they will do: Update product backlog,Complete first app release implementation. Create domain model & detailed design document.
What impediments prevent them from progressing: Difficulty with implementation, other classwork, Still not feeling well
| Vasilis | What they have done: Completed work for saving/loading schedules
What they will do: Update platform & SRS/Use case model document. Created GRL & UCM models document. Complete first app release implementation.
What impediments prevent them from progressing: Other classwork
| Yong | What they have done: Began working on map interface implementation.
What they will do: Create GRL & UCM models document. Complete first app release implementation.
What impediments prevent them from progressing: Difficulty with implementation, other classwork
Meeting 2 | 2018-03-08
| Arpit | What they have done: No work completed.
What will they do: Not present for scrum meeting.
What impediments prevent them from progressing: Not present for scrum meeting.
| Brody | What they have done: Miscellaneous documentation tasks, Updated SRS and UML document, Created configuration management plan document.
What they will do: Enjoy spring break
What impediments prevent them from progressing: N/A
| Michael | What they have done: Completed detailed design and domain model document, completed first few user interface implementations.
What they will do: Enjoy spring break
What impediments prevent them from progressing: N/A
| Sakshyam | What they have done: Completed first few user interface implementations
What they will do: Enjoy spring break
What impediments prevent them from progressing: N/A
| Vasilis | What they have done: Completed first few user interface implementations, Miscellaneous implementation fixes, Implemented story number 4, Updated SRS and UML document, Worked on GRL and UCM model document. Created configuration management plan.
What they will do: Enjoy spring break
What impediments prevent them from progressing: N/A
| Yong | What they have done: Worked on GRL and UCM model document. Implemented showing route between start and destination points.
What they will do: Enjoy spring break
What impediments prevent them from progressing: N/A
END OF SPRINT

## Sprint 4
Daily Scrum Report — Sprint 4
Kanban board is ZenHub. Use the ZenHub browser extension to view the RaiderNAV Kanban board in GitHub.
Meetings are for development team, product owner, and scrum master.
Each team member should report: what they have done, what they will do, and what impediments prevent them from progressing.
Meeting 1 | 2018-03-20
| Arpit | What they have done: | Attended meeting, planned implementation of more user stories
|  | What they will do: | Implement a functionality to add temporary locations to the app.
What impediments prevent them from progressing:
| Brody | What they have done: | Attended meeting, planned implementation of more user stories
|  | What they will do: | Design the app to determine location of buildings matching TTU database
What impediments prevent them from progressing:
| Michael | What they have done: | Attended meeting, planned implementation of more user stories
|  | What they will do: | Create a verification screen for delete button in deleteSchedule.
What impediments prevent them from progressing:
| Sakshyam | What they have done: | Attended meeting, planned implementation of more user stories
|  | What they will do: | Add a privacy policy message , Update Daily Scrum Report, Update Kanban Board, Update Team Member report, Create Sprint Backlog.
What impediments prevent them from progressing:
| Vasilis | What they have done: | Attended meeting, planned implementation of more user stories
|  | What they will do: | Implement quickfind feature on the app, Create product backlog.
What impediments prevent them from progressing:
| Yong | What they have done: | Attended meeting, planned implementation of more user stories
|  | What they will do: | Implement code to show the shortest route possible at all times
What impediments prevent them from progressing:
Meeting 2 | 2018-03-30
| Arpit | What they have done: | Working on implementing a functionality to add temporary food locations, more tasks discussed and divided.
|  | What they will do: | Start with creation of a Test plan document.Update SRS and Use Case models document.Update GRL and UCM Models document.
What impediments prevent them from progressing:
| Brody | What they have done: | Implemented the app to determine location of buildings matching TTU database, more tasks discussed and divided.
|  | What they will do: | Start creating a Software Architecture and Design Pattern Document. Update SRS and Use Case models document.Update GRL and UCM Models document.
What impediments prevent them from progressing:
| Michael | What they have done: | Created a verification screen for delete schedule button, more tasks discussed and divided.
|  | What they will do: | Update the domain model and detailed design document. Update SRS and Use Case models document.Update GRL and UCM Models document.
What impediments prevent them from progressing:
| Sakshyam | What they have done: | Implemented a one time welcome screen with privacy notice, updated zenhub board, updated scrum report and sprint backlog.
|  | What they will do: | Start creating a Software Architecture and Design Pattern Document. Update SRS and Use Case models document.Update GRL and UCM Models document.
What impediments prevent them from progressing:
| Vasilis | What they have done: | Implemented a quickfind feature in the homescreen of the application, more tasks discussed and divided.
|  | What they will do: | Update Configuration Management document, Update platform Document. Update SRS and Use Case models document.Update GRL and UCM Models document.
What impediments prevent them from progressing:
| Yong | What they have done: | Working on implementing code to show the shortest walking route during navigation.
|  | What they will do: | Start creating a Test plan document. Update SRS and Use Case models document.Update GRL and UCM Models document.
What impediments prevent them from progressing:
END OF SPRINT

## Sprint 5
Daily Scrum Report — Sprint 5
Kanban board is ZenHub. Use the ZenHub browser extension to view the RaiderNAV Kanban board in GitHub.
Meetings are for development team, product owner, and scrum master.
Each team member should report: what they have done, what they will do, and what impediments prevent them from progressing.
Meeting 1 | 2018-04-01
| Arpit | What they have done: | None
|  | What they will do: | Unit test
|  | What impediments prevent them from progressing: |  | Sick
| Brody | What they have done: | Sprint 5 backlog update; Update UCM SRS GRL for user story 5
|  | What they will do: | GRL analysis
|  | What impediments prevent them from progressing: |  | N/A
| Michael | What they have done: | Conduct usability study
|  | What they will do: | Create usability study document, implement user story 30
|  | What impediments prevent them from progressing: |  | AthletesTraveling
| Sakshyam | What they have done: | Update URN document user story 21
|  | What they will do: | Update SRS document for user story 21
|  | What impediments prevent them from progressing: |  | N/A
| Vasilis | What they have done: | Update plateform document, SRS, URN
|  | What they will do: | Implement user story 2, 34
|  | What impediments prevent them from progressing: |  | N/A
| Yong | What they have done: | Implementing user store 8
|  | What they will do: | Finish user store 8 implementation; Arrange team meetings; Working on test plan documentation
|  | What impediments prevent them from progressing: |  | N/A
Meeting 2 | 2018-04-06
| Arpit | What they have done: | None
|  | What they will do: | Unit test
|  | What impediments prevent them from progressing: |  | Sick
| Brody | What they have done: | GRL analysis ; Updated configuration management plan document.
|  | What they will do: | Working on Software Architecture and Design Pattern Document
|  | What impediments prevent them from progressing: |  | N/A
| Michael | What they have done: | Conduct usability study, user story 30 implementation
|  | What they will do: | Record usability study
|  | What impediments prevent them from progressing: |  | AthletesTraveling
| Sakshyam | What they have done: | Update SRS document for user story 21
|  | What they will do: | Working on Software Architecture and Design Pattern Document
|  | What impediments prevent them from progressing: |  | N/A
| Vasilis | What they have done: | Implement user story 2, 34
|  | What they will do: | Update URN document, create test plan document
|  | What impediments prevent them from progressing: |  | N/A
| Yong | What they have done: | Working on documentations for deliverable 3 Sprint 5; Working as scrum master during Sprint 5
|  | What they will do: | Finish implementation for user story 8; Submit deliverable 5 documentations
|  | What impediments prevent them from progressing: |  | N/A
END OF SPRINT