## Sprint 1
SPRINT BACKLOG — Deliverable 1
Each sprint on a separate sheet, one user story per row – created before sprint 1 and updated at a minimum of once a day during the sprint.
Progress tracked on ZenHub Kanban board.
Story Types: F (functional), NF (non-functional)
Story Subtypes: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal and Number | Story | Story Type | Story Subtype | Story Points | Story Points Completed | Team Member Names and Percentage Contribution to the Story
This sprint is focused on documentation.
8, complete permission form | N/A | N/A | T | 1 | 1 | Vasilis: 100%
7, complete sprint review document | N/A | N/A | T | 1 | 1 | Vasilis: 100%
20, create document for team member report | N/A | N/A | T | 1 | 1 | Vasilis: 100%
5, create platform document | N/A | N/A | T | 1 | 1 | Vasilis: 100%
23, create use cases for stories 1-3 | 1-3 | N/A | T | 3 | 3 | Sakshyam: 100%
26, create use cases for stories 10-12 and 19 | 10-12, 19 | N/A | T | 4 | 4 | Yong: 100%
13, expand user stories 1-3 into requirements | 1-3 | N/A | T | 3 | 3 | Sakshyam: 100%
10, create interview scripts | N/A | N/A | T | 3 | 3 | Brody: 100%
16, expand user stories 10-12 and 19 into requirements | 10-12, 19 | N/A | T | 4 | 4 | Yong: 100%
17, expand user stories 13-15 into requirements | 13-15 | N/A | T | 3 | 3 | Vasilis: 100%
27, create use cases for stories 13-15 | 13-15 | N/A | T | 3 | 3 | Vasilis: 100%
15, expand user stories 7-9 into requirements | 7-9 | N/A | T | 3 | 3 | Michael: 100%
3, create document for product backlog | N/A | N/A | T | 4 | 4 | Arpit, Brody, Michael, Sakshyam, Vasilis, Yong: 100%
19, create document for sprint backlog | N/A | N/A | T | 2 | 2 | Vasilis: 100%
25, create use cases for stories 7-9 | 7-9 | N/A | T | 3 | 3 | Michael: 100%
24, create use cases for stories 4-6 | 4-6 | N/A | T | 3 | 3 | Brody: 80%, Michael, Sakshyam: 20%
14, expand user stories 4-6 into requirements | 4-6 | N/A | T | 3 | 3 | Brody: 100%
28, create use cases for stories 16 and 17 | 16-17 | N/A | T | 2 | 2 | Brody: 100%, Arpit: 0%
18, expand user stories 16 and 17 into requirements | 16-17 | N/A | T | 2 | 2 | Brody: 100%, Arpit: 0%
35, expand user stories 18 and 20 into requirements | 18 and 20 | N/A | T | 2 | 2 | Yong: 100%, Arpit: 0%
36, create use cases for stories 18 and 20 | 18 and 20 | N/A | T | 2 | 2 | Yong: 100%, Arpit: 0%
9, complete product mockup | N/A | N/A | T | 5 | 5 | Michael, Sakshyam: 100%
6, create SRS/use case document | N/A | N/A | T | 6 | 6 | Vasilis: 90%, Arpit, Brody, Michael, Sakshyam, Yong: 10%
4, create focus group document | N/A | N/A | T | 6 | 6 | Brody, Michael, Sakshyam: 100%
21, update sprint review document before finalizing sprint | N/A | N/A | T | 1 | 1 | Vasilis: 100%
22, update team member report before finalizing sprint | N/A | N/A | T | 1 | 1 | Vasilis: 100%

## Sprint 2
SPRINT #2 BACKLOG
Each sprint on a separate sheet, one user story per row – created before sprint 2 and updated at a minimum of once a day during the sprint.
Story Types: F (functional), NF (non-functional)
Story Subtypes: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal and Number | Story | Story Type | Story Subtype | Story Points | Story Points Completed | Team Member Names and Percentage Contribution to the Story
42, Complete preparation of proposal slideshow | N/A | N/A | T | 5 | 5 | Yong, Vasilis, Arpit, Michael, Sakshyam: 100%
47, Update product backlog for beginning of Sprint 2 | N/A | N/A | T | 2 | 2 | Sakshyam: 100%
45, Update daily scrum report | N/A | N/A | T | 2 | 2 | Brody: 100%
48, Update sprint backlog for beginning of sprint 2 | N/A | N/A | T | 2 | 2 | Brody: 100%
79, Conduct Focus Group | N/A | N/A | T | 6 | 6 | Yong, Vasilis, Arpit, Michael, Sakshyam, Brody: 100%
43, Organize Focus Group | N/A | N/A | T | 3 | 3 | Michael: 100%
46, Finish focus group document | N/A | N/A | T | 5 | 5 | Brody: 100%
50, Update platform document | N/A | N/A | T | 4 | 4 | Vasilis: 100%
58, Implement backend functionality for saving and recalling saved schedules | 2,3 | F | T | 5 | 5 | Vasilis: 100%
59, Implement data structure for mapping building prefixes to physical addresses | 1,5 | F | T | 4 | 4 | Brody: 100%
44, Complete Sprint 2 Review Document | N/A | N/A | T | 2 | 2 | Brody: 100%
49, Update team member report | N/A | N/A | T | 2 | 2 | Brody: 100%

## Sprint 3
SPRINT #3 BACKLOG
Each sprint on a separate sheet, one user story per row – created before sprint 2 and updated at a minimum of once a day during the sprint.
Story Types: F (functional), NF (non-functional)
Story Subtypes: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal and Number | Story | Story Type | Story Subtype | Story Points | Story Points Completed | Team Member Names and Percentage Contribution to the Story
45, Update daily scrum report | N/A | N/A | T | 2 | 2 | Brody: 100%
48, Update sprint backlog for beginning of sprint 3 | N/A | N/A | T | 2 | 2 | Brody: 100%
51, Update SRS and UML document | N/A | N/A | T | 8 | 8 | Brody, Vasilis: 100%
53, Create Domain Model and Detailed Design Model document | N/A | N/A | T | 5 | 5 | Michael: 100%
54, Create Configuration Management Plan document | N/A | N/A | T | 5 | 5 | Yong, Vasilis, Brody: 100%
55, Create GRL and UCM Models Document | N/A | N/A | T | 6 | 6 | Yong, Vasilis: 100%
56, Create user interface for creating a schedule, adding classes, and saving a schedule | 1,2 | F | T | 4 | 4 | Michael, Sakshyam, Vasilis: 100%
57, Create user interface for recalling schedules, schedule selection, and detail display | 2,3 | F | T | 4 | 4 | Michael, Sakshyam, Vasilis: 100%
61, Implement front end for route display after API calls to generate route | 1,5 | F | T | 4 | 4 | Yong: 100%
49, Update team member report | N/A | N/A | T | 2 | 2 | Brody: 100%
44, Complete Sprint 3 Review Document | N/A | N/A | T | 2 | 2 | Brody: 100%
75, Finalize sprint 3 backlog | N/A | N/A | T | 1 | 1 | Brody: 100%

## Sprint 4
SPRINT #4 BACKLOG
Each sprint on a separate sheet, one user story per row – created before sprint 2 and updated at a minimum of once a day during the sprint.
Story Types: F (functional), NF (non-functional)
Story Subtypes: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal and Number | Story | Story Type | Story Subtype | Story Points | Story Points Completed | Team Member Names and Percentage Contribution to the Story
102, Update Daily Scrum Report | N/A | N/A | T | 2 | 2 | Sakshyam: 100%
103, Update Product backlog | N/A | N/A | T | 2 | 2 | Vasilis: 100%
104, Update Sprint Backlog | N/A | N/A | T | 2 | 2 | Sakshyam: 100%
98, Add a quickfind feature on the homescreen | 24 | F | T | 6 | 6 | Vasilis: 100%
95, Create a privacy policy message on the welcome screen | 21 | F | T | 1 | 1 | Sakshyam: 100%
97, Implement the app to determine location of buildings matching TTU database | 5 | F | T | 4 |  | Brody: 100%
99, Implement code to show the shortest walking route during navigation | 8 | F | T | 1
100, Create a verificatin screen for delete schedule button | 30 | F | T | 1 |  | Micheal: 100%
101, Implement a functionallity to add temporary locations | 16 | F | T | 1
105, Update Team Member Report | N/A | N/A | T | 2 |  | Sakshyam: 100%
106, Complete Sprint 4 Review Document | N/A | N/A | T | 2 |  | Sakshyam: 100%
118, Create Sprint 5 review document | N/A | N/A | T | 2 | 2 | Sakshyam: 100%
144, Update SRS and UC document document for User story 30 | 30 | F | T | 2 | 2 | Micheal: 100%
148, Update SRS and UC document document for User story 24 | 24 | F | T | 2 | 2 | Vasilis: 100%
162, Restructure URN document | N/A | N/A | T | 3 | 3 | Vasilis: 100%
164,Create use case maps for schedule actions | N/A | N/A | T | 5 | 5 | Vasilis: 100%
119, Update Configuration management plan document | N/A | N/A | T | 3 | 3 | Vasilis: 100%
114, Update Platform Document | N/A | N/A | T | 1 | 1 | Vasilis: 100%
140, update grl and ucm model document for user story #24 | 24 | F | T | 2 | 2 | Vasilis: 100%
137, update grl and ucm model document for user story #21 | 21 | F | T | 2 | 2 | Sakshyam: 100%
138, update grl and ucm model document for user story #30 | 30 | F | T | 2 | 2 | Micheal: 100%
160, Add unscheduled navigation scenario to URN document | N/A | F | T | 2 | 2 | Vasilis: 100%
161, Add edit course scenario to URN document | N/A | F | T | 2 | 2 | Vasilis: 100%

## Sprint 5
SPRINT #5 BACKLOG
Each sprint on a separate sheet, one user story per row – created before sprint 2 and updated at a minimum of once a day during the sprint.
Story Types: F (functional), NF (non-functional)
Story Subtypes: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal and Number | Story | Story Type | Story Subtype | Story Points | Story Points Completed | Team Member Names and Percentage Contribution to the Story
193, TOC and PDF-ize Test Plan document | N/A | N/A | T | 1 | 1 | Brody 100%
121, Complete test plan document | N/A | N/A | T | 4 | 4 | Vasilis,Yong 100%
221, Create misuse case diagram for story 34 | 34 | F | T | 2 | 2 | Vasilis 100%
191, Complete use case testing | N/A | N/A | T | 3 | 3 | Yong 100%
217, Implement TA's 11th-hour Suggestions | N/A | N/A | T | 4 | 4 | Vasilis, Brody 100%
220, PDFize SRS (again) | N/A | N/A | T | 1 | 1 | Brody 100%
222, Complete requirements in SRS for story 34 | 34 | F | T | 2 | 2 | Brody 100%
219, Add use case for story 34 to SRS | 34 | F | T | 3 | 3 | Brody 100%
218, Add misuse case diagram to SRS | N/A | N/A | T | 1 | 1 | Brody 100%
110, Finalize product backlog | N/A | N/A | T | 1 | 1 | Vasilis, Brody 100%
216, Add story 34 to product backlog | 34 | F | T | 1 | 1 | Brody 100%
157, Regenerate TOC and PDF-ize SRS document | N/A | N/A | T | 1 | 1 | Brody 100%
154, Replace old mockups in SRS | N/A | N/A | T | 2 | 2 | Brody, Michael 100%
189, Create APK release for deliverable 3 | N/A | N/A | T | 1 | 1 | Vasilis 100%
143, Update SRS and UC document for User Story 8 | 8 | F | T | 2 | 2 | Yong 100%
145, Update SRS and UC document for User Story 21 | 21 | F | T | 2 | 2 | Sakshyam 100%
117, Update GRL and UCM document | N/A | N/A | T | 1 | 1 | Michael, Sakshyam, Vasilis, Brody, Yong 100%
116, Update SRS and UC document | N/A | N/A | T | 4 | 4 | Michael, Sakshyam, Vasilis, Brody, Yong 100%
142, update grl and ucm model document for user story #8 | 8 | F | T | 1 | 1 | Yong 100%
99, implement user story 8 | 8 | F | T | 1 | 1 | Yong 100%
146, Update SRS and UC document for User Story 5 | 5 | F | T | 2 | 2 | Brody 100%
176, Update Product backlog for start of Sprint 5 | N/A | N/A | T | 1 | 1 | Brody 100%
174, Reword privacy notification text | N/A | N/A | T | 1 | 1 | Vasilis 100%
139, update grl and ucm model document for user story #5 | 5 | F | T | 2 | 2 | Brody 100%
172, Regenerate scenarios after UCM completed | N/A | N/A | T | 1 | 1 | Vasilis 100%
153, Regenerate TOC and PDF-ize SCMP | N/A | N/A | T | 1 | 1 | Brody 100%
184, Combine script, blank consent, signed consent, results, notes, & conclusions into Usability document | N/A | N/A | T | 3 | 3 | Vasilis 100%
182, Ensure submittable URN.jucm is latest iteration | N/A | N/A | T | 1 | 1 | Vasilis 100%
180, Generate TOC and PDF-ize URN document | N/A | N/A | T | 1 | 1 | Brody 100%
115, Update domain model & detailed design document | N/A | N/A | T | 1 | 1 | Michael, Sakshyam, Vasilis, Brody, Yong 100%
120, Create and PDFize software architecture and design pattern document | N/A | N/A | T | 4 | 4 | Brody 100%
192, Complete acceptance testing | N/A | N/A | T | 1 | 1 | Vasilis 100%
190, Complete unit testing | N/A | N/A | T | 3 | 3 | Vasilis, Sakshyam 100%
122, Complete usability study document | N/A | N/A | T | 5 | 5 | Vasilis 100%
208, Fill in UCM blanks on URN document | N/A | N/A | T | 3 | 3 | Brody 100%
207, Fill in GRL blanks on URN document | N/A | N/A | T | 3 | 3 | Brody 100%
186, Create usability study forms | N/A | N/A | T | 2 | 2 | Brody, Vasilis 100%
159, Fill in the blanks on URN document | N/A | N/A | T | 3 | 3 | Brody 100%
185, Perform usability study | N/A | N/A | T | 3 | 3 | Michael, Sakshyam, Vasilis, Brody, Yong 100%
102, finalize scrum report | N/A | N/A | T | 1 | 1 | Yong 100%
214, sprint backlog | N/A | N/A | T | 2 | 2 | Yong 100%
136, team member report | N/A | N/A | T | 1 | 1 | Yong 100%
118, complete sprint 5 review | N/A | N/A | T | 1 | 1 | Yong, Brody 100%

## Sprint 6
SPRINT #6 BACKLOG
Each sprint on a separate sheet, one user story per row – created before sprint 2 and updated at a minimum of once a day during the sprint.
Story Types: F (functional), NF (non-functional)
Story Subtypes: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal and Number | Story | Story Type | Story Subtype | Story Points | Story Points Completed | Team Member Names and Percentage Contribution to the Story
147, 141 Update SRS and URN | 16 | T | T | 3 | 3 | Arpit: 100%