## Sprint 4
PRODUCT BACKLOG — DELIVERABLE 3
One user story per row. This document must be updated at minimum at the beginning and end of sprints.
Keep sorted by priority.
ID | Story | Sprint | Story Priority | Story Status | Story Points
24 | As a user, I want a quick-find feature so that I can find the nearest path to a single destination without inputting a schedule. | 4 |  | D | 6 | ← from focus group
30 | As a user, I want to be asked to verify before a schedule or course is deleted, so that I do not accidentally delete a schedule. | 4 |  | D | 1 | ← from focus group
5 | As a user, I want the app to automatically determine the geographical location of buildings that my classes are in based only on the name of the building as provided by the schedule in the TTU registration system, so that I can easily have my schedule generated without research or prior knowledge of where the buildings are. | 4 |  | D | 4
21 | As a user, I want to be presented with a message the first time I load the app that informs me of the privacy implications of using the app, so that I am aware of how my information is being handled. | 4 | H, 1 | IP | 1
8 | As a user, I want the app to show me the shortest walking route between classes, so that I can arrive as quickly as possible in the event that I am running late. | 4 | H, 2 | IP | 1
16 | As a user, I want to be able to arbitrarily add some other locations to the app and to my schedules, so that I can plan in regular lunch destinations or walks for exercise between classes. | 4 | H, 3 | IP | 3
6 | As a user, I want the app to intelligently determine when classes for the day are already over and provide the reduced set of directions only to classes which are not yet over, so that I am not encumbered by excess, unnecessary information. | undecided | H, 4 | W | 2
15 | As a user, I want the app to recalculate the shortest path to the next destination in my schedule with the push of a ‘recalculate’ button, in the event that I veer from the original route and require new directions. | undecided | H, 5 | W | 1
10 | As a user, I want the app to show me an estimated amount of time to travel from my current location to the next destination in my schedule, so that I can react with more urgency if I am in danger of being late. | undecided | H, 6 | W | 2
11 | As a user, I want the app to tell me how much time is available until my next class begins, so that I can more easily fit unscheduled activities into my day without calculating myself the amount of time available until class begins. | undecided | M, 7 | W | 3
12 | As a user, I want the app to notify me with special messages when I am in danger of being late to class, based on the time the class begins and the travel time necessary to reach the building, so that I can afford to be distracted and do not have to constantly check the app. | undecided | M, 8 | W | 5
13 | As a user, I want the reminder feature to honor silent mode and notification settings on the mobile device, so that I am not inconvenienced by additional settings. | undecided | M, 9 | W | 1
14 | As a user, I want to be able to completely disable all reminder features, regardless of phone notification settings on the mobile device, so that I am not bothered by unnecessary reminders when I am confident about my schedule. | undecided | M, 10 | W | 2
32 | As a user, I want to select times for my courses from a dropdown menu, so that I can easily set the time without error or knowledge about the internal time format for the app. | undecided | M, 11 | W | 3
23 | As a user, I want the app to show me shortest paths which include bus routes, so that I can reach very far destinations on campus quickly. | undecided | L, 12 | W | 6 | ← from presentation feedback
33 | As a user, I want to be able to review the privacy policy/implications statement at any time, preferably from within the settings menu, so that do not have to take special measures to review the statement if I have forgotten its contents. | undecided | L, 13 | W | 1
26 | As a user, I want the app to collect a minimal amount of private information about me to perform its work, so that I maintain control of my private information. | undecided | L, 14 | W | 6 | ← from deliverable 0 feedback
31 | As a user, I want the ability to share a location with others who do not have the app, so that I can easily communicate an intended location to friends. | undecided | L, 15 | W | 6
27 | As a user, I want the app to be secure, so that information collected by the app is not shared with unintended parties. | undecided | L, 16 | W | 7 | ← from deliverable 0 feedback
25 | As a user, I want the ability to share a location with another user of the app, so that I can easily communicate an intended location to friends. | undecided | L, 17 | W | 9 | ← from deliverable 0 feedback
18 | As a user, I want to be able to mark a class as temporarily canceled for the day, so that I do not receive unnecessary notifications, reminders, or directions for classes I will not be attending that day. | undecided | L, 18 | W | 4
7 | As a user, I also want the app to give me the option to toggle showing the routes to ALL classes for the day regardless of whether they are already over, so that I can show my schedule to others in person. | undecided | L, 19 | W | 4
9 | As a user, I want the app to regularly update and display my current location on the navigation map, so that I can more easily follow the directions provided by the app. | undecided | L, 20 | W | 2
17 | As a user, I want to be able to add arbitrary locations which will only be considered on that day only, and not saved to the schedule for use on other days, so that I can benefit from the features of the app even with short-term plans without inconveniencing myself by having to remove destinations from the schedule again later. | undecided | L, 21 | W | 4
28 | As a user, I want to be able to set date ranges for entered schedules, so past schedules will automatically be removed. | undecided | L, 22 | W | 2 | ← from focus group
20 | As a user, I want to be able to export schedules to other common digital calendar formats, so that I can integrate some benefits from the app with other apps that I use every day. | undecided | L, 23 | W | 7
22 | As a user, I want the app to show me the nearest vending machine location at the push of a button, so that I can avoid excessive travel when I am hungry/thirsty. | undecided | L, 24 | W | 5 | ← Arpit’s idea
COMPLETED
1 | As a user, I want to be able to add my class schedule (course building, time) for the day to the app, so that I can receive complete and correct walking directions to each building in order from the app. | 2 |  | D | 3
2 | As a user, I want to be able to save my schedule for the day and give it a name so that I can recall it quickly in the future. | 2 |  | D | 3
3 | As a user, I want to be able to save and recall multiple schedules, because I may not have the same schedule every day. | 2 |  | D | 3
4 | As a user, I want to be able to easily delete saved schedules, in case my schedule changes or I have progressed to a new term with different classes, so that I am not encumbered by schedules that are no longer relevant. | 2 |  | D | 2
29 | As a user, I want to be able to name each schedule myself, so that they are customized to my needs. | 1 |  | D | 3 | ← from focus group
19 | As a user, I want to be able to edit existing/saved schedules to change the buildings and times of each class, so that I can correct for schedule changes and prior input mistakes without creating entirely new schedules. | 2 |  | D | 3
| Story Priorities: | H (high) | M (medium) | L (low)
| Story Statuses: | W (waiting) | IP (in progress) | T (testing) | D (done)

## Sprint 5
PRODUCT BACKLOG — DELIVERABLE 3
One user story per row. This document must be updated at minimum at the beginning and end of sprints.
Keep sorted by priority.
ID | Story | Sprint | Story Priority | Story Status | Story Points
21 | As a user, I want to be presented with a message the first time I load the app that informs me of the privacy implications of using the app, so that I am aware of how my information is being handled. | 5 | H, 1 | IP | 1
8 | As a user, I want the app to show me the shortest walking route between classes, so that I can arrive as quickly as possible in the event that I am running late. | 5 | H, 2 | IP | 1
16 | As a user, I want to be able to arbitrarily add some other locations to the app and to my schedules, so that I can plan in regular lunch destinations or walks for exercise between classes. | 5 | H, 3 | IP | 3
6 | As a user, I want the app to intelligently determine when classes for the day are already over and provide the reduced set of directions only to classes which are not yet over, so that I am not encumbered by excess, unnecessary information. | undecided | H, 4 | W | 2
15 | As a user, I want the app to recalculate the shortest path to the next destination in my schedule with the push of a ‘recalculate’ button, in the event that I veer from the original route and require new directions. | undecided | H, 5 | W | 1
10 | As a user, I want the app to show me an estimated amount of time to travel from my current location to the next destination in my schedule, so that I can react with more urgency if I am in danger of being late. | undecided | H, 6 | W | 2
11 | As a user, I want the app to tell me how much time is available until my next class begins, so that I can more easily fit unscheduled activities into my day without calculating myself the amount of time available until class begins. | undecided | M, 7 | W | 3
12 | As a user, I want the app to notify me with special messages when I am in danger of being late to class, based on the time the class begins and the travel time necessary to reach the building, so that I can afford to be distracted and do not have to constantly check the app. | undecided | M, 8 | W | 5
13 | As a user, I want the reminder feature to honor silent mode and notification settings on the mobile device, so that I am not inconvenienced by additional settings. | undecided | M, 9 | W | 1
14 | As a user, I want to be able to completely disable all reminder features, regardless of phone notification settings on the mobile device, so that I am not bothered by unnecessary reminders when I am confident about my schedule. | undecided | M, 10 | W | 2
32 | As a user, I want to select times for my courses from a dropdown menu, so that I can easily set the time without error or knowledge about the internal time format for the app. | undecided | M, 11 | W | 3
23 | As a user, I want the app to show me shortest paths which include bus routes, so that I can reach very far destinations on campus quickly. | undecided | L, 12 | W | 6 | ← from presentation feedback
33 | As a user, I want to be able to review the privacy policy/implications statement at any time, preferably from within the settings menu, so that do not have to take special measures to review the statement if I have forgotten its contents. | undecided | L, 13 | W | 1
26 | As a user, I want the app to collect a minimal amount of private information about me to perform its work, so that I maintain control of my private information. | undecided | L, 14 | W | 6 | ← from deliverable 0 feedback
31 | As a user, I want the ability to share a location with others who do not have the app, so that I can easily communicate an intended location to friends. | undecided | L, 15 | W | 6
27 | As a user, I want the app to be secure, so that information collected by the app is not shared with unintended parties. | undecided | L, 16 | W | 7 | ← from deliverable 0 feedback
25 | As a user, I want the ability to share a location with another user of the app, so that I can easily communicate an intended location to friends. | undecided | L, 17 | W | 9 | ← from deliverable 0 feedback
18 | As a user, I want to be able to mark a class as temporarily canceled for the day, so that I do not receive unnecessary notifications, reminders, or directions for classes I will not be attending that day. | undecided | L, 18 | W | 4
7 | As a user, I also want the app to give me the option to toggle showing the routes to ALL classes for the day regardless of whether they are already over, so that I can show my schedule to others in person. | undecided | L, 19 | W | 4
9 | As a user, I want the app to regularly update and display my current location on the navigation map, so that I can more easily follow the directions provided by the app. | undecided | L, 20 | W | 2
17 | As a user, I want to be able to add arbitrary locations which will only be considered on that day only, and not saved to the schedule for use on other days, so that I can benefit from the features of the app even with short-term plans without inconveniencing myself by having to remove destinations from the schedule again later. | undecided | L, 21 | W | 4
28 | As a user, I want to be able to set date ranges for entered schedules, so past schedules will automatically be removed. | undecided | L, 22 | W | 2 | ← from focus group
20 | As a user, I want to be able to export schedules to other common digital calendar formats, so that I can integrate some benefits from the app with other apps that I use every day. | undecided | L, 23 | W | 7
22 | As a user, I want the app to show me the nearest vending machine location at the push of a button, so that I can avoid excessive travel when I am hungry/thirsty. | undecided | L, 24 | W | 5 | ← Arpit’s idea
COMPLETED
1 | As a user, I want to be able to add my class schedule (course building, time) for the day to the app, so that I can receive complete and correct walking directions to each building in order from the app. | 2 |  | D | 3
2 | As a user, I want to be able to save my schedule for the day and give it a name so that I can recall it quickly in the future. | 2 |  | D | 3
3 | As a user, I want to be able to save and recall multiple schedules, because I may not have the same schedule every day. | 2 |  | D | 3
4 | As a user, I want to be able to easily delete saved schedules, in case my schedule changes or I have progressed to a new term with different classes, so that I am not encumbered by schedules that are no longer relevant. | 2 |  | D | 2
29 | As a user, I want to be able to name each schedule myself, so that they are customized to my needs. | 1 |  | D | 3 | ← from focus group
19 | As a user, I want to be able to edit existing/saved schedules to change the buildings and times of each class, so that I can correct for schedule changes and prior input mistakes without creating entirely new schedules. | 2 |  | D | 3
24 | As a user, I want a quick-find feature so that I can find the nearest path to a single destination without inputting a schedule. | 4 |  | D | 6 | ← from focus group
30 | As a user, I want to be asked to verify before a schedule or course is deleted, so that I do not accidentally delete a schedule. | 4 |  | D | 1 | ← from focus group
5 | As a user, I want the app to automatically determine the geographical location of buildings that my classes are in based only on the name of the building as provided by the schedule in the TTU registration system, so that I can easily have my schedule generated without research or prior knowledge of where the buildings are. | 4 |  | D | 4
| Story Priorities: | H (high) | M (medium) | L (low)
| Story Statuses: | W (waiting) | IP (in progress) | T (testing) | D (done)