## Sprint 1
Daily Scrum Report — Sprint 1
Kanban board is ZenHub. Use the ZenHub browser extension to view the RaiderNAV Kanban board in GitHub.
Meetings are for development team, and maybe scrum master.
Meetings will be conducted each Wednesday and Saturday, and over email if in-person meetings are not possible.
Each team member should report: what they have done, what they will do, and what impediments prevent them from progressing.
Meeting 1 | 7 Feb 18
| Arpit | What they have done: |  | Joined GitHub project
|  | What they will do: |  | Break down user stories 16-18 and 20. Install ZenHub. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Brody | What they have done: |  | Joined GitHub project and installed ZenHub.
|  | What they will do: |  | Break down user stories 4-6. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Michael | What they have done: |  | Joined GitHub project and installed ZenHub.
|  | What they will do: |  | Break down user stories 7-9. Product mockup. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Sakshyam | What they have done: |  | Joined GitHub project and installed ZenHub.
|  | What they will do: |  | Break down user stories 1-3. Product mockup. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Vasilis | What they have done: |  | Joined GitHub project and installed ZenHub.
|  | What they will do: |  | Break down user stories 13-15. Permission form. Other unscheduled documents.
What impediments prevent them from progressing:
| Yong | What they have done: |  | Joined GitHub project and installed ZenHub.
|  | What they will do: |  | Break down user stories 10-12 and 19. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
Meeting 2 | 10 Feb 18
| Arpit | What they have done: |  | Absent from meeting
|  | What will they do: |  | Learn how to do use cases, install UMLet, install Android Studio, install ZenHub
What impediments prevent them from progressing:
| Brody | What they have done: | Installed Androi | Installed Android Studio, reqs and use cases for 4-6, interview scripts
|  | What they will do: |  | Update interview script
|  | What impediments prevent them from progressing: |  | None
| Michael | What they have done: |  | Installed Android Studio, reqs and use cases for 7-9
|  | What they will do: |  | Mockup
|  | What impediments prevent them from progressing: |  | None
| Sakshyam | What they have done: |  | Installed Android Studio, reqs and use cases for 1-3
|  | What they will do: |  | Mockup
|  | What impediments prevent them from progressing: |  | None
| Vasilis | What they have done: |  | reqs and use cases for stories 13-15, permission form, created various documents
What they will do:
|  | What impediments prevent them from progressing: |  | None
| Yong | What they have done: |  | Installed Android Studio, reqs and use cases for 10-12 and 18-20
What they will do:
|  | What impediments prevent them from progressing: |  | None
Meeting 3 | 12 Feb 18
| Arpit | What they have done: |  | Installed Android Studio, Installed UMLet, Installed ZenHub, Installed GitKraken
|  | What they will do: |  | SRS document
|  | What impediments prevent them from progressing: |  | Not knowing how to do use cases
| Brody | What they have done:
|  | What they will do: |  | Focus Group document
|  | What impediments prevent them from progressing: |  | None
| Michael | What they have done: |  | Product Mockup
|  | What they will do: |  | Focus Group document
|  | What impediments prevent them from progressing: |  | None
| Sakshyam | What they have done: |  | Product Mockup
|  | What they will do: |  | Focus Group document
|  | What impediments prevent them from progressing: |  | None
| Vasilis | What they have done:
|  | What they will do: |  | SRS document
|  | What impediments prevent them from progressing: |  | None
| Yong | What they have done:
|  | What they will do: |  | SRS document
What impediments prevent them from progressing:
Meeting 4 | 13 Feb 18
| Arpit | What they have done: |  | Absent from meeting
What they will do:
What impediments prevent them from progressing:
| Brody | What they have done: |  | Focus Group document, SRS document
What they will do:
|  | What impediments prevent them from progressing: |  | None
| Michael | What they have done: |  | Focus Group document, SRS document
What they will do:
|  | What impediments prevent them from progressing: |  | None
| Sakshyam | What they have done: |  | Focus Group document, SRS document
What they will do:
|  | What impediments prevent them from progressing: |  | None
| Vasilis | What they have done: |  | SRS document
What they will do:
|  | What impediments prevent them from progressing: |  | None
| Yong | What they have done: |  | SRS document
What they will do:
|  | What impediments prevent them from progressing: |  | None
END OF SPRINT

## Sprint 2
Daily Scrum Report — Sprint 2
Kanban board is ZenHub. Use the ZenHub browser extension to view the RaiderNAV Kanban board in GitHub.
Meetings are for development team, product owner, and scrum master.
Each team member should report: what they have done, what they will do, and what impediments prevent them from progressing.
Meeting 1 | 2018-02-16
| Arpit | What they have done: Project Proposal Presentation
What they will do: Attend next meeting 2/18
What impediments prevent them from progressing: N/A
| Brody | What they have done: Update Kanban Board, Update Daily Scrum Report, Update Sprint Backlog
What they will do: What they will do: Attend next meeting 2/18
What impediments prevent them from progressing: N/A
| Michael | What they have done: Project Proposal Presentation
What they will do: Organize focus groups participants and meeting time
What impediments prevent them from progressing: N/A
| Sakshyam | What they have done: Update Product Backlog for start of Sprint 2
What they will do: Attend next meeting 2/18
What impediments prevent them from progressing: N/A
| Vasilis | What they have done: Project Propsosal Presentation
What they will do: Attend next meeting 2/18
What impediments prevent them from progressing: N/A
| Yong | What they have done: Project Proposal Presentation
What they will do: Attend next meeting 2/18
What impediments prevent them from progressing: N/A
Meeting 2 | 2018-02-18
| Arpit | What they have done:
What will they do:
What impediments prevent them from progressing:
| Brody | What they have done:
What they will do:
What impediments prevent them from progressing:
| Michael | What they have done:
What they will do:
What impediments prevent them from progressing:
| Sakshyam | What they have done:
What they will do:
What impediments prevent them from progressing:
| Vasilis | What they have done:
What they will do:
What impediments prevent them from progressing:
| Yong | What they have done:
What they will do:
What impediments prevent them from progressing:
Meeting 3 | xx Feb 18
| Arpit | What they have done:
What they will do:
What impediments prevent them from progressing:
| Brody | What they have done:
What they will do:
What impediments prevent them from progressing:
| Michael | What they have done:
What they will do:
What impediments prevent them from progressing:
| Sakshyam | What they have done:
What they will do:
What impediments prevent them from progressing:
| Vasilis | What they have done:
What they will do:
What impediments prevent them from progressing:
| Yong | What they have done:
What they will do:
What impediments prevent them from progressing:
Meeting 4 | xx Feb 18
| Arpit | What they have done:
What they will do:
What impediments prevent them from progressing:
| Brody | What they have done:
What they will do:
What impediments prevent them from progressing:
| Michael | What they have done:
What they will do:
What impediments prevent them from progressing:
| Sakshyam | What they have done:
What they will do:
What impediments prevent them from progressing:
| Vasilis | What they have done:
What they will do:
What impediments prevent them from progressing:
| Yong | What they have done:
What they will do:
What impediments prevent them from progressing:
END OF SPRINT

## Sprint 3
Daily Scrum Report — Sprint 3
Kanban board is ZenHub. Use the ZenHub browser extension to view the RaiderNAV Kanban board in GitHub.
Meetings are for development team, and maybe scrum master.
Meetings will be conducted each Wednesday and Saturday, and over email if in-person meetings are not possible.
Each team member should report: what they have done, what they will do, and what impediments prevent them from progressing.
Meeting 1 | xx Feb 18 | (for this sprint, everyone is on the development team, but this should not be the usual)
| Arpit | What they have done:
What they will do:
What impediments prevent them from progressing:
| Brody | What they have done:
What they will do:
What impediments prevent them from progressing:
| Michael | What they have done:
What they will do:
What impediments prevent them from progressing:
| Sakshyam | What they have done:
What they will do:
What impediments prevent them from progressing:
| Vasilis | What they have done:
What they will do:
What impediments prevent them from progressing:
| Yong | What they have done:
What they will do:
What impediments prevent them from progressing:
Meeting 2 | xx Feb 18
| Arpit | What they have done:
What will they do:
What impediments prevent them from progressing:
| Brody | What they have done:
What they will do:
What impediments prevent them from progressing:
| Michael | What they have done:
What they will do:
What impediments prevent them from progressing:
| Sakshyam | What they have done:
What they will do:
What impediments prevent them from progressing:
| Vasilis | What they have done:
What they will do:
What impediments prevent them from progressing:
| Yong | What they have done:
What they will do:
What impediments prevent them from progressing:
Meeting 3 | xx Feb 18
| Arpit | What they have done:
What they will do:
What impediments prevent them from progressing:
| Brody | What they have done:
What they will do:
What impediments prevent them from progressing:
| Michael | What they have done:
What they will do:
What impediments prevent them from progressing:
| Sakshyam | What they have done:
What they will do:
What impediments prevent them from progressing:
| Vasilis | What they have done:
What they will do:
What impediments prevent them from progressing:
| Yong | What they have done:
What they will do:
What impediments prevent them from progressing:
Meeting 4 | xx Feb 18
| Arpit | What they have done:
What they will do:
What impediments prevent them from progressing:
| Brody | What they have done:
What they will do:
What impediments prevent them from progressing:
| Michael | What they have done:
What they will do:
What impediments prevent them from progressing:
| Sakshyam | What they have done:
What they will do:
What impediments prevent them from progressing:
| Vasilis | What they have done:
What they will do:
What impediments prevent them from progressing:
| Yong | What they have done:
What they will do:
What impediments prevent them from progressing:
END OF SPRINT