## Sheet1
Daily Scrum Report
Kanban board is ZenHub. Use the ZenHub browser extension to view the RaiderNAV Kanban board in GitHub.
Meetings are for development team, and maybe scrum master.
Meetings will be conducted each Wednesday and Saturday, and over email if in-person meetings are not possible.
Each team member should report: what they have done, what they will do, and what impediments prevent them from progressing.
Meeting 1 | 7 Feb 18 | (for this sprint, everyone is on the development team, but this should not be the usual)
| Arpit | What they have done: | Joined GitHub project
|  | What they will do: | Break down user stories 16-18 and 20. Install ZenHub. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Brody | What they have done: | Joined GitHub project and installed ZenHub.
|  | What they will do: | Break down user stories 4-6. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Michael | What they have done: | Joined GitHub project and installed ZenHub.
|  | What they will do: | Break down user stories 7-9. Product mockup. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Sakshyam | What they have done: | Joined GitHub project and installed ZenHub.
|  | What they will do: | Break down user stories 1-3. Product mockup. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Vasilis | What they have done: | Joined GitHub project and installed ZenHub.
|  | What they will do: | Break down user stories 13-15. Permission form. Other unscheduled documents.
What impediments prevent them from progressing:
| Yong | What they have done: | Joined GitHub project and installed ZenHub.
|  | What they will do: | Break down user stories 10-12 and 19. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
Meeting 2 | 10 Feb 18
| Arpit | What they have done: Absent from meeting
What they will do:
What impediments prevent them from progressing: None
| Brody | What they have done: Installed Android Studio, Reqs and Use Cases for stories 4-6
What they will do: interview scripts
What impediments prevent them from progressing:
| Michael | What they have done: Installed Android Studio, Reqs for 7-9
What they will do: use cases for 7-9, mockup
What impediments prevent them from progressing: None
| Sakshyam | What they have done: Installed Android Studio, user reqs for 1-3
What they will do: system reqs and use cases for 1-3, mockup
What impediments prevent them from progressing: None
| Vasilis | What they have done: reqs and use cases for stories 13-15, permission form, created various documents
What they will do:
What impediments prevent them from progressing: None
| Yong | What they have done: Installed Android Studio, reqs for 10-12 and 19
What they will do: use cases for 10-19 and 19
What impediments prevent them from progressing: None
Meeting 3 | xx Feb 18
| Arpit | What they have done:
What they will do:
What impediments prevent them from progressing:
| Brody | What they have done:
What they will do:
What impediments prevent them from progressing:
| Michael | What they have done:
What they will do:
What impediments prevent them from progressing:
| Sakshyam | What they have done:
What they will do:
What impediments prevent them from progressing:
| Vasilis | What they have done:
What they will do:
What impediments prevent them from progressing:
| Yong | What they have done:
What they will do:
What impediments prevent them from progressing: