## Sprint 1
SPRINT BACKLOG — Deliverable 1
Each sprint on a separate sheet, one user story per row – created before sprint 1 and updated at a minimum of once a day during the sprint.
Progress tracked on ZenHub Kanban board.
Story Types: F (functional), NF (non-functional)
Story Subtypes: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal and Number | Story | Story Type | Story Subtype | Story Points | Story Points Completed | Team Member Names and Percentage Contribution to the Story
This sprint is focused on documentation.
8, complete permission form | N/A | N/A | T | 1 | 1 | Vasilis: 100%
7, complete sprint review document | N/A | N/A | T | 1 | 1 | Vasilis: 100%
20, create document for team member report | N/A | N/A | T | 1 | 1 | Vasilis: 100%
5, create platform document | N/A | N/A | T | 1 | 1 | Vasilis: 100%
23, create use cases for stories 1-3 | 1-3 | N/A | T | 3 | 3 | Sakshyam: 100%
26, create use cases for stories 10-12 and 19 | 10-12, 19 | N/A | T | 4 | 4 | Yong: 100%
13, expand user stories 1-3 into requirements | 1-3 | N/A | T | 3 | 3 | Sakshyam: 100%
10, create interview scripts | N/A | N/A | T | 3 | 3 | Brody: 100%
16, expand user stories 10-12 and 19 into requirements | 10-12, 19 | N/A | T | 4 | 4 | Yong: 100%
17, expand user stories 13-15 into requirements | 13-15 | N/A | T | 3 | 3 | Vasilis: 100%
27, create use cases for stories 13-15 | 13-15 | N/A | T | 3 | 3 | Vasilis: 100%
15, expand user stories 7-9 into requirements | 7-9 | N/A | T | 3 | 3 | Michael: 100%
3, create document for product backlog | N/A | N/A | T | 4 | 4 | Arpit, Brody, Michael, Sakshyam, Vasilis, Yong: 100%
19, create document for sprint backlog | N/A | N/A | T | 2 | 2 | Vasilis: 100%
25, create use cases for stories 7-9 | 7-9 | N/A | T | 3 | 3 | Michael: 100%
24, create use cases for stories 4-6 | 4-6 | N/A | T | 3 | 3 | Brody: 80%, Michael, Sakshyam: 20%
14, expand user stories 4-6 into requirements | 4-6 | N/A | T | 3 | 3 | Brody: 100%
28, create use cases for stories 16 and 17 | 16-17 | N/A | T | 2 | 2 | Brody: 100%, Arpit: 0%
18, expand user stories 16 and 17 into requirements | 16-17 | N/A | T | 2 | 2 | Brody: 100%, Arpit: 0%
35, expand user stories 18 and 20 into requirements | 18 and 20 | N/A | T | 2 | 2 | Yong: 100%, Arpit: 0%
36, create use cases for stories 18 and 20 | 18 and 20 | N/A | T | 2 | 2 | Yong: 100%, Arpit: 0%
9, complete product mockup | N/A | N/A | T | 5 | 5 | Michael, Sakshyam: 100%
6, create SRS/use case document | N/A | N/A | T | 6 | 6 | Vasilis: 90%, Arpit, Brody, Michael, Sakshyam, Yong: 10%
4, create focus group document | N/A | N/A | T | 6 | 6 | Brody, Michael, Sakshyam: 100%
21, update sprint review document before finalizing sprint | N/A | N/A | T | 1 | 1 | Vasilis: 100%
22, update team member report before finalizing sprint | N/A | N/A | T | 1 | 1 | Vasilis: 100%

## Sprint 2
SPRINT #2 BACKLOG
Each sprint on a separate sheet, one user story per row – created before sprint 2 and updated at a minimum of once a day during the sprint.
Story Types: F (functional), NF (non-functional)
Story Subtypes: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal and Number | Story | Story Type | Story Subtype | Story Points | Story Points Completed | Team Member Names and Percentage Contribution to the Story
42, Complete preparation of proposal slideshow | N/A | N/A | T | 5 | 5 | Yong, Vasilis, Arpit, Michael, Sakshyam: 100%
47, Update product backlog for beginning of Sprint 2 | N/A | N/A | T | 2 | 2 | Sakshyam: 100%
45, Update daily scrum report | N/A | N/A | T | 2 | 2 | Brody: 100%
48, Update sprint backlog for beginning of sprint 2 | N/A | N/A | T | 2 | 2 | Brody: 100%
79, Conduct Focus Group | N/A | N/A | T | 6 | 6 | Yong, Vasilis, Arpit, Michael, Sakshyam, Brody: 100%
43, Organize Focus Group | N/A | N/A | T | 3 | 3 | Michael: 100%
46, Finish focus group document | N/A | N/A | T | 5 | 5 | Brody: 100%
50, Update platform document | N/A | N/A | T | 4 | 4 | Vasilis: 100%
58, Implement backend functionality for saving and recalling saved schedules | 2,3 | F | T | 5 | 5 | Vasilis: 100%
59, Implement data structure for mapping building prefixes to physical addresses | 1,5 | F | T | 4 | 4 | Brody: 100%
44, Complete Sprint 2 Review Document | N/A | N/A | T | 2 | 2 | Brody: 100%
49, Update team member report | N/A | N/A | T | 2 | 2 | Brody: 100%

## Sprint 3
SPRINT #3 BACKLOG
Each sprint on a separate sheet, one user story per row – created before sprint 2 and updated at a minimum of once a day during the sprint.
Story Types: F (functional), NF (non-functional)
Story Subtypes: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal and Number | Story | Story Type | Story Subtype | Story Points | Story Points Completed | Team Member Names and Percentage Contribution to the Story
45, Update daily scrum report | N/A | N/A | T | 2 | 2 | Brody: 100%
48, Update sprint backlog for beginning of sprint 3 | N/A | N/A | T | 2 | 2 | Brody: 100%
51, Update SRS and UML document | N/A | N/A | T | 8 | 8 | Brody, Vasilis: 100%
53, Create Domain Model and Detailed Design Model document | N/A | N/A | T | 5 | 5 | Michael: 100%
54, Create Configuration Management Plan document | N/A | N/A | T | 5 | 5 | Yong, Vasilis, Brody: 100%
55, Create GRL and UCM Models Document | N/A | N/A | T | 6 | 6 | Yong, Vasilis: 100%
56, Create user interface for creating a schedule, adding classes, and saving a schedule | 1,2 | F | T | 4 | 4 | Michael, Sakshyam, Vasilis: 100%
57, Create user interface for recalling schedules, schedule selection, and detail display | 2,3 | F | T | 4 | 4 | Michael, Sakshyam, Vasilis: 100%
61, Implement front end for route display after API calls to generate route | 1,5 | F | T | 4 | 4 | Yong: 100%
49, Update team member report | N/A | N/A | T | 2 | 2 | Brody: 100%
44, Complete Sprint 3 Review Document | N/A | N/A | T | 2 | 2 | Brody: 100%
75, Finalize sprint 3 backlog | N/A | N/A | T | 1 | 1 | Brody: 100%

## Sprint 4
SPRINT #4 BACKLOG
Each sprint on a separate sheet, one user story per row – created before sprint 2 and updated at a minimum of once a day during the sprint.
Story Types: F (functional), NF (non-functional)
Story Subtypes: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal and Number | Story | Story Type | Story Subtype | Story Points | Story Points Completed | Team Member Names and Percentage Contribution to the Story
102, Update Daily Scrum Report | N/A | N/A | T | 2 | 2 | Sakshyam: 100%
103, Update Product backlog | N/A | N/A | T | 2 | 2 | Vasilis: 100%
104, Update Sprint Backlog | N/A | N/A | T | 2 | 2 | Sakshyam: 100%
98, Add a quickfind feature on the homescreen | 24 | F | T | 6
95, Create a privacy policy message on the welcome screen | 21 | F | T | 1
97, Implement the app to determine location of buildings matching TTU database | 5 | F | T | 2
99, Implement code to show the shortest walking route during navigation | 8 | F | T | 1
100, Create a verificatin screen for delete schedule button | 30 | F | T | 1
101, Implement a functionallity to add temporary locations | 16 | F | T | 1
105, Update Team Member Report | N/A | N/A | T | 2
106, Complete Sprint 4 Review Document | N/A | N/A | T | 2