## Sprint 1
Daily Scrum Report
Kanban board is ZenHub. Use the ZenHub browser extension to view the RaiderNAV Kanban board in GitHub.
Meetings are for development team, and maybe scrum master.
Meetings will be conducted each Wednesday and Saturday, and over email if in-person meetings are not possible.
Each team member should report: what they have done, what they will do, and what impediments prevent them from progressing.
Meeting 1 | 7 Feb 18 | (for this sprint, everyone is on the development team, but this should not be the usual)
| Arpit | What they have done: | Joined GitHub project
|  | What they will do: | Break down user stories 16-18 and 20. Install ZenHub. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Brody | What they have done: | Joined GitHub project and installed ZenHub.
|  | What they will do: | Break down user stories 4-6. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Michael | What they have done: | Joined GitHub project and installed ZenHub.
|  | What they will do: | Break down user stories 7-9. Product mockup. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Sakshyam | What they have done: | Joined GitHub project and installed ZenHub.
|  | What they will do: | Break down user stories 1-3. Product mockup. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
| Vasilis | What they have done: | Joined GitHub project and installed ZenHub.
|  | What they will do: | Break down user stories 13-15. Permission form. Other unscheduled documents.
What impediments prevent them from progressing:
| Yong | What they have done: | Joined GitHub project and installed ZenHub.
|  | What they will do: | Break down user stories 10-12 and 19. Install UMLet. Install Android Studio.
What impediments prevent them from progressing:
Meeting 2 | 10 Feb 18
| Arpit | What they have done:
What will they do: Learn how to do use cases, install UMLet, install Android Studio, install ZenHub
What impediments prevent them from progressing:
| Brody | What they have done: Installed Android Studio, reqs and use cases for 4-6, interview scripts
What they will do: Update interview script
What impediments prevent them from progressing: None
| Michael | What they have done: Installed Android Studio, reqs and use cases for 7-9
What they will do: mockup
What impediments prevent them from progressing: None
| Sakshyam | What they have done: Installed Android Studio, reqs and use cases for 1-3
What they will do: mockup
What impediments prevent them from progressing: None
| Vasilis | What they have done: reqs and use cases for stories 13-15, permission form, created various documents
What they will do:
What impediments prevent them from progressing: None
| Yong | What they have done: Installed Android Studio, reqs and use cases for 10-12 and 18-20
What they will do:
What impediments prevent them from progressing: None
Meeting 3 | 12 Feb 18
| Arpit | What they have done: Installed Android Studio, Installed UMLet, Installed ZenHub, Installed GitKraken
What they will do: SRS document
What impediments prevent them from progressing: Not knowing how to do use cases
| Brody | What they have done:
What they will do: Focus Group document
What impediments prevent them from progressing: None
| Michael | What they have done: Product Mockup
What they will do: Focus Group document
What impediments prevent them from progressing: None
| Sakshyam | What they have done: Product Mockup
What they will do: Focus Group document
What impediments prevent them from progressing: None
| Vasilis | What they have done:
What they will do: SRS document
What impediments prevent them from progressing:
| Yong | What they have done:
What they will do: SRS document
What impediments prevent them from progressing:
Meeting 4 | 13 Feb 18
| Arpit | What they have done:
What they will do:
What impediments prevent them from progressing:
| Brody | What they have done: Focus Group document
What they will do:
What impediments prevent them from progressing: None
| Michael | What they have done: Focus Group document
What they will do:
What impediments prevent them from progressing: None
| Sakshyam | What they have done: Focus Group document
What they will do:
What impediments prevent them from progressing: None
| Vasilis | What they have done: SRS doc
What they will do:
What impediments prevent them from progressing: None
| Yong | What they have done:
What they will do:
What impediments prevent them from progressing: None