## Sprint 1
SPRINT BACKLOG
Each sprint on a separate sheet, one user story per row – created before sprint 1 and updated at a minimum of once a day during the sprint.
Progress tracked on ZenHub Kanban board.
Story Types: F (functional), NF (non-functional)
Story Subtypes: B (bug), T (technical work), KA (knowledge acquisition)
Sprint Goal and Number | Story | Story Type | Story Subtype | Story Points | Story Points Completed | Team Member Names and Percentage Contribution to the Story
This sprint is focused on documentation.
8, complete permission form | N/A | N/A | T | 1 | 1 | Vasilis, 100%
7, complete sprint review document | N/A | N/A | T | 1 | 1 | Vasilis, 100%
20, create document for team member report | N/A | N/A | T | 1 | 1 | Vasilis, 100%
5, create platform document | N/A | N/A | T | 1 | 1 | Vasilis, 100%
23, create use cases for stories 1-3 | 1-3 | N/A | T | 3 | 3 | Sakshyam, 100%
26, create use cases for stories 10-12 and 19 | 10-12, 19 | N/A | T | 4 | 4 | Yong, 100%
13, expand user stories 1-3 into requirements | 1-3 | N/A | T | 3 | 3 | Sakshyam, 100%
10, create interview scripts | N/A | N/A | T | 3 | 3 | Brody, 100%
16, expand user stories 10-12 and 19 into requirements | 10-12, 19 | N/A | T | 4 | 4 | Yong, 100%
17, expand user stories 13-15 into requirements | 13-15 | N/A | T | 3 | 3 | Vasilis, 100%
27, create use cases for stories 13-15 | 13-15 | N/A | T | 3 | 3 | Vasilis, 100%
15, expand user stories 7-9 into requirements | 7-9 | N/A | T | 3 | 3 | Michael, 100%
3, create document for product backlog | N/A | N/A | T | 4 | 4 | Arpit, Brody, Michael, Sakshyam, Vasilis, Yong: 100%
19, create document for sprint backlog | N/A | N/A | T | 2 | 2 | Vasilis, 100%
25, create use cases for stories 7-9 | 7-9 | N/A | T | 3 | 3 | Michael, 100%
24, create use cases for stories 4-6 | 4-6 | N/A | T | 3 | 3 | Brody, 100%
14, expand user stories 4-6 into requirements | 4-6 | N/A | T | 3 | 3 | Brody, 100%
28, create use cases for stories 16 and 17 | 16-17 | N/A | T | 2 |  | Brody:
18, expand user stories 16 and 17 into requirements | 16-17 | N/A | T | 2 |  | Brody:
35, expand user stories 18 and 20 into requirements | 18 and 20 | N/A | T | 2 |  | Yong:
36, create use cases for stories 18 and 20 | 18 and 20 | N/A | T | 2 |  | Yong:
9, complete product mockup | N/A | N/A | T | 3 |  | Michael, Sakshyam:

## Sprint 2
SPRINT BACKLOG
Each sprint on a separate sheet, one user story per row – created before sprint 1 and updated at a minimum of once a day during the sprint.
Sprint Goal and Number | Story | Story Type | Story Subtype | Story Points | Story Points Completed | Team Member Names and Percentage Contribution to the Story
Story Types: F (functional), NF (non-functional)
Story Subtypes: B (bug), T (technical work), KA (knowledge acquisition)