## Sprint 6
Daily Scrum Report — Sprint 2
Kanban board is ZenHub. Use the ZenHub browser extension to view the RaiderNAV Kanban board in GitHub.
Meetings are for development team, product owner, and scrum master.
Each team member should report: what they have done, what they will do, and what impediments prevent them from progressing.
Meeting 1 | 2018-04-26
| Arpit | What they have done: Set up the foundation for the final presentation
What they will do: Slide #1 and #2 for the Final Presentation
What impediments prevent them from progressing: N/A
| Brody | What they have done: Set up the foundation for the final presentation
What they will do: The will complete slides #4, #5, #10, #11, and #15 for the Final Presentation
What impediments prevent them from progressing: N/A
| Michael | What they have done: Set up the foundation for the final presentation
What they will do: Slides #8 #9 #18 #20 for the Final Presentation
What impediments prevent them from progressing: N/A
| Sakshyam | What they have done: Set up the foundation for the final presentation
What they will do: Slides #12 #19 #21#25 #26 for the Final Presentation
What impediments prevent them from progressing: N/A
| Vasilis | What they have done:Set up the foundation for the final presentation
What they will do: Slides #12 #13 #16 #17 #22 for the Final Presentation
What impediments prevent them from progressing: N/A
| Yong | What they have done: Set up the foundation for the final presentation
What they will do: Slides #3 #6 #7 #14 #23 for the Final Presentation
What impediments prevent them from progressing: N/A
Meeting 2 | 2018-04-30
| Arpit | What they have done: Completed Slides 1 and 2
What they will do: Prepare for the presentation. Assist in the completion with the SRS and UC documents and also the Future Implementation Plan Document
What impediments prevent them from progressing: N/A
| Brody | What they have done:Completed Slides 4, 5, 10, 11, and 15.
What they will do: Prepare for the presentation. Assist in the completion with the SRS and UC documents and also the Future Implementation Plan Document
What impediments prevent them from progressing: N/A
| Michael | What they have done: Completed Slides 8, 9, 18, and 20.
What they will do: Prepare for the presentation. Assist in the completion with the SRS and UC documents and also the Future Implementation Plan Document. Finalize the Sprint Backlog and Sprint Review.
What impediments prevent them from progressing: N/A
| Sakshyam | What they have done: Completed Slides 12, 19, 21, 25, and 26.
What they will do: Prepare for the presentation. Assist in the completion with the SRS and UC documents and also the Future Implementation Plan Document
What impediments prevent them from progressing: N/A
| Vasilis | What they have done: Completed Slides 12, 13, 16, 17, and 22.
What they will do: Prepare for the presentation. Assist in the completion with the SRS and UC documents and also the Future Implementation Plan Document
What impediments prevent them from progressing: N/A
| Yong | What they have done: Completed Slides 3, 6, 7, 14, and 23.
What they will do: Prepare for the presentation. Assist in the completion with the SRS and UC documents and also the Future Implementation Plan Document
What impediments prevent them from progressing: N/A
Meeting 3 | 2018-05-09
| Arpit | What they have done: Implented User story 16, updated the URN document for story 16, and updated the SRS document for user story 16, Finalize the SRS and UC document.
What they will do:
What impediments prevent them from progressing: N/A
| Brody | What they have done: Finalized the Architecture design document, Completed the test plan document and the TOC/PDFuze SCMP, Updated the SRS screenshots, and Recorded the app demo videos, Finalize the SRS and UC document, Completed the TOC and PDFize SRS and Finalize the URN document.
What they will do:
What impediments prevent them from progressing: N/A
| Michael | What they have done: Finalized the detailed design document and did the daily scrum report, Finalize the SRS and UC document, Update and Finalize the Sprint Backlog and Finalize the Team member report, the sprint review document, and the daily scrum report.
What they will do:
What impediments prevent them from progressing: N/A
| Sakshyam | What they have done: Finalize the SRS and UC document
What they will do:
What impediments prevent them from progressing: N/A
| Vasilis | What they have done: Completed the configuration management plan document, reworded the safety requirements in SRS, Fixed the initial run permission crash, Updated the colors/layout of the app, Fixed the zoom, created the final APK release, added the testing section to the platform document, and finalized the platform document, Finalize the SRS and UC document and will create the remaining tasks and future implementation plan document.
What they will do:
What impediments prevent them from progressing: N/A
| Yong | What they have done: Updated the product backlog, Finalize the SRS and UC document and Finalize the product backlog.
What they will do:
What impediments prevent them from progressing: N/A
END OF SPRINT