## Arpit
Team Member Report – Sprint 1
One sheet per team member name for every sprint. Updated for every sprint.
Team member name: | Arpit
Roles played this week: | Development Team
Role duties and work performed this week, artifacts created/updated/reviewed: | Contributed to product backlog prioritization; Contributed to SRS document
Role duties and work to be performed next week: | Development Team
Issues encountered: | Scheduling conflicts; Communication issues
Issues resolved: | Scheduling conflicts

## Brody
Team Member Report – Sprint 1
One sheet per team member name for every sprint. Updated for every sprint.
Team member name: | Brody
Roles played this week: | Development Team
Role duties and work performed this week, artifacts created/updated/reviewed: | Created interview scripts; Contributed to product backlog prioritization; Created use cases for stories 4-6 and 16-17; Expanded user stories 4-6 and 16-17 into requirements; Contributed to SRS document; Contributed to Focus Group document
Role duties and work to be performed next week: | Scrum Master
Issues encountered: | None
Issues resolved: | N/A

## Michael
Team Member Report – Sprint 1
One sheet per team member name for every sprint. Updated for every sprint.
Team member name: | Michael
Roles played this week: | Product Owner
Role duties and work performed this week, artifacts created/updated/reviewed: | Expanded user stories 7-9 into requirements; Created use cases for stories 7-9; Contributed to product backlog prioritization (most vocal); Contributed to use cases 4-6 and 16-17; Contributed to product mockup; Contributed to SRS document; Contributed to Focus Group document
Role duties and work to be performed next week: | Development Team
Issues encountered: | None
Issues resolved: | N/A

## Sakshyam
Team Member Report – Sprint 1
One sheet per team member name for every sprint. Updated for every sprint.
Team member name: | Sakshyam
Roles played this week: | Development Team
Role duties and work performed this week, artifacts created/updated/reviewed: | Created use cases for stories 1-3; Expanded user stories 1-3 into requirements; Contributed to product backlog prioritization; contributed to use cases for stories 4-6; Contributed to SRS document; Contributed to focus group document
Role duties and work to be performed next week: | Product Owner
Issues encountered: | None
Issues resolved: | N/A

## Vasilis
Team Member Report – Sprint 1
One sheet per team member name for every sprint. Updated for every sprint.
Team member name: | Vasilis
Roles played this week: | Scrum Master
Role duties and work performed this week, artifacts created/updated/reviewed: | Did permission form, sprint review document, team member report document, platform document, sprint backlog document; Expanded user stories 13-15 into requirements; Created use cases for stories 13-15; Contributed to product backlog prioritization; Created product backlog document; did SRS document
Role duties and work to be performed next week: | Development Team
Issues encountered: | None
Issues resolved: | N/A

## Yong
Team Member Report – Sprint 1
One sheet per team member name for every sprint. Updated for every sprint.
Team member name: | Yong
Roles played this week: | Development Team
Role duties and work performed this week, artifacts created/updated/reviewed: | Created use cases for stories 10-12 and 18-20; Expanded user stories 10-12 and 18-20 into requirements; Contributed to product backlog prioritization; Contributed to SRS document
Role duties and work to be performed next week: | Development Team
Issues encountered: | None
Issues resolved: | N/A